🧩 Optimized Technical Requirements (for 3-person team)

This version trims complexity while keeping the platform scalable.

1. Architecture (Simplified for small team)

Node.js handles:

- API Gateway

- Tenant management

- Auth (JWT)

- VA routing + conversation storage

- IDP job orchestration

- Image processing job orchestration

- Workflow engine (basic rules)

- Admin dashboard backend

Python handles:

- NLP/LLM prompt pipelines

- OCR + document parsing

- CV models (classification/detection)

- Vector DB operations (if used)

- Model fine-tuning scripts

Shared components:

- PostgreSQL (tenant data, logs, configs)

- S3-compatible storage (docs/images)

- Redis (queues + caching)

- Lightweight event bus (Redis streams or simple pub/sub)

This keeps the system modular without overwhelming the team.

🧑‍💻 Team Roles (3-Person Setup)

Engineer 1 — Full-Stack / Backend (Node.js Lead)

- API gateway

- Tenant management

- VA routing service

- Workflow engine

- Admin dashboard backend

- DevOps (CI/CD, containers, infra)

Engineer 2 — ML/AI Engineer (Python Lead)

- NLP pipelines for VA

- OCR + NLP for IDP

- CV model integration

- Vector DB (optional MVP)

- Model evaluation + fine-tuning

Engineer 3 — Frontend + Integrations

- Admin dashboard UI (React)

- Document upload UI

- Image upload UI

- Workflow rule builder UI

- Embeddable VA widget

This division ensures no one is overloaded and each person owns a vertical slice.

🗂️ Refined 12-Week Developer Sprint Plan (3-Person Team)

This is optimized for velocity and realism.

Sprint 1 (Weeks 1–2): Platform Skeleton + Infrastructure

Engineer 1 (Node)

- Set up monorepo or multi-repo structure

- Build API gateway skeleton

- Implement JWT auth

- Create tenant/user models in PostgreSQL

- Set up Redis + S3 buckets

Engineer 2 (Python)

- Set up Python service structure

- Evaluate OCR (Tesseract vs AWS Textract vs Google Vision)

- Evaluate CV model options

- Build first VA prompt templates

Engineer 3 (Frontend)

- Create React admin dashboard skeleton

- Implement login page + JWT handling

- Basic navigation layout

Deliverable:
Platform boots end-to-end with login, empty dashboard, and working API gateway.

Sprint 2 (Weeks 3–4): Virtual Assistant MVP

Engineer 1 (Node)

- Build VA API endpoints

- Conversation logging

- Tenant-specific VA config

Engineer 2 (Python)

- Build NLP pipeline (prompt templates + intent extraction)

- Integrate with LLM provider

- Build healthcare VA template (first vertical)

Engineer 3 (Frontend)

- VA configuration UI

- Conversation viewer UI

Deliverable:
Working Virtual Assistant for healthcare with configurable intents.

Sprint 3 (Weeks 5–6): IDP MVP (OCR + NLP)

Engineer 1 (Node)

- Document upload endpoint

- Async job queue (Redis)

- Document status tracking

Engineer 2 (Python)

- OCR pipeline

- Entity extraction for invoices/contracts

- Document classification

Engineer 3 (Frontend)

- Document upload UI

- Processed document viewer

Deliverable:
Upload → OCR → Extract → View results.

Sprint 4 (Weeks 7–8): Image Processing MVP + Analytics

Engineer 1 (Node)

- Image upload endpoint

- CV job orchestration

Engineer 2 (Python)

- Integrate CV model (YOLOv8 or similar)

- Build classification/detection pipeline

Engineer 3 (Frontend)

- Image upload UI

- Basic analytics dashboard (usage metrics)

Deliverable:
Image classification/detection working + analytics tiles.

Sprint 5 (Weeks 9–10): Workflow Engine (Basic)

Engineer 1 (Node)

- Rule engine (if X then Y)

- Webhook triggers

- Event bus integration

Engineer 2 (Python)

- Add event hooks to VA, IDP, CV pipelines

Engineer 3 (Frontend)

- Simple rule builder UI (dropdowns, not full no-code)

Deliverable:
“When invoice processed → send webhook” works end-to-end.

Sprint 6 (Weeks 11–12): Hardening + Pilot Readiness

Engineer 1 (Node)

- Rate limiting

- Logging + monitoring

- Performance tuning

Engineer 2 (Python)

- Improve extraction accuracy

- Add fallback prompts

- Add confidence scoring

Engineer 3 (Frontend)

- UI polish

- Error states

- Usage export (CSV)

Deliverable:
Pilot-ready MVP for first 3–5 SME clients.

🎯 What This Plan Achieves

With only 3 engineers, you still deliver:

- Virtual Assistant MVP

- IDP MVP

- Image Processing MVP

- Workflow engine

- Admin dashboard

- Analytics

- Multi-tenant architecture

- Pilot-ready product in 12 weeks

This is exactly the kind of roadmap investors love:
ambitious but realistic, modular, and revenue-ready.